## Scheduled
Date | Time Start | Time End | Venue | PM | Province | Municipality | Target | SSDG Count | SSDG Personnel | IT Personnel | Vehicle
2026-01-19 | 8:00 | 12:00 PM | LASLASONG NORTE COVERED COURT, STA MARIA | HBR | ILOCOS SUR | STA MARIA | 124 | 4 | Kriztel, Rudel, Mark Jayson, Jonathan | Richard, Kristine, Erol | Pool Car
2026-01-19 | 8:00 | 12:00 PM | BRGY KALUMSING COVERED COURT | ADM | ILOCOS SUR | SAN EMILIO | 84 | 3 | Angelo, Recel, Dan | Harry | Pool Car
2026-01-19 | 8:00 | 12:00 PM | BUGNAY BARANGAY PLAZA | RVR | ILOCOS SUR | CANDON | 94 | 4 | Natasha, Joy-Anne, Rodante, Renante | Yolie | Pool Car
2026-01-19 | 8:00 | 12:00 PM | MABUTI BARANGAY HALL | WDS | ILOCOS NORTE | MARCOS | 81 | 3 | Jerson, Ryan, Noble |  | Motor
2026-01-19 | 8:00 | 12:00 PM | SAN JUAN MUNICIPAL HALL | AGN | ABRA | SAN JUAN | 65 | 4 | Gilbert, Cherry, Blessie, John Rey |  | Motor
2026-01-19 | 8:30 | 12:00 PM | ESTER BRGY HALL | MDL | ILOCOS NORTE | VINTAR | 215 | 5 | Joel, Glenn, Arvee, Jayzer, Erl |  | Motor
2026-01-19 | 9:00 | 12:00 PM | SACRITAN BARANGAY HALL, SACRITAN, PINILI, ILOCOS NORTE | WDM | ILOCOS NORTE | PINILI | 173 | 5 | We-Ann, Arnelyn, Limwel, Alma, Domerson | Rogen | Pool Car
2026-01-19 | 13:00 | 5:00 PM | ALLANGIGAN SEGUNDO BARANGAY PLAZA | RVR | ILOCOS SUR | CANDON | 41 | 4 | Natasha, Joy-Anne, Rodante, Renante | Yolie | Pool Car
2026-01-19 | 13:00 | 5:00 PM | FL RAYMOND BERONILLA RESIDENCE SALUCAG, DOLORES | AGN | ABRA | DOLORES | 29 | 2 | Gilbert, Blessie |  | Motor
2026-01-19 | 13:00 | 5:00 PM | IMELDA-CAPARIAAN BARANGAY HALL | WDS | ILOCOS NORTE | MARCOS | 46 | 3 | Jerson, Ryan, Noble |  | Motor
2026-01-19 | 13:00 | 5:00 PM | KINABITI, PILAR BRGY. HALL | AGN | ABRA | PILAR | 29 | 2 | Cherry, John Rey |  | Motor
2026-01-19 | 13:00 | 5:00 PM | LILIPUTEN BARANGAY HALL, LILIPUTEN, PINILI, ILOCOS NORTE | WDM | ILOCOS NORTE | PINILI | 46 | 5 | We-Ann, Arnelyn, Limwel, Alma, Domerson | Rogen | Pool Car
2026-01-19 | 13:30 | 5:00 PM | BRGY SIBSIBBU COVERED COURT | ADM | ILOCOS SUR | SAN EMILIO | 22 | 3 | Angelo, Recel, Dan | Harry | Pool Car
2026-01-19 | 14:00 | 5:00 PM | SAN NICOLAS DA OFFICE | MDL | ILOCOS NORTE | SAN NICOLAS | 90 | 5 | Joel, Glenn, Arvee, Jayzer, Erl |  | Motor
2026-01-20 | 8:00 | 12:00 PM | NAGSAYAOAN COVERED COURT, STA MARIA | HBR | ILOCOS SUR | NARVACAN, STA MARIA | 116 | 4 | Kriztel, Rudel, Mark Jayson, Jonathan | Richard, Kristine | Pool Car
2026-01-20 | 8:30 | 12:00 PM | MUNICIPAL COVERED COURT,NAGBUKEL I.S | RSG | ILOCOS SUR | NAGBUKEL, NARVACAN | 242 | 8 | Natasha, Joy-Anne, Rodante, Renante, Angelo, Recel, Dan, Domerson | Erol, Harry, Yolie | Pool Car
2026-01-20 | 8:00 | 12:00 PM | VELASCO, TAYUM BRGY. HALL | AGN | ABRA | TAYUM | 124 | 4 | Gilbert, Cherry, Blessie, John Rey |  | Motor
2026-01-20 | 8:30 | 12:00 PM | LAOAG CITY DA OFFICE | MDL | ILOCOS NORTE | LAOAG | 98 | 4 | Joel, Glenn, Arvee, Jayzer |  | Motor
2026-01-20 | 8:30 | 12:00 PM | SUCSUQUEN BRGY HALL | MDL | ILOCOS NORTE | PIDDIG | 96 | 4 | Jerson, Ryan, Noble, Erl |  | Motor
2026-01-20 | 9:00 | 12:00 PM | SALANAP BARANGAY HALL, SALANAP, PINILI, ILOCOS NORTE | WDM | ILOCOS NORTE | PINILI | 85 | 4 | We-Ann, Arnelyn, Limwel, Alma | Rogen | Pool Car
2026-01-20 | 13:00 | 5:00 PM | BANGBANGAR COVERED COURT | ACM | ILOCOS SUR | BURGOS | 67 | 4 | *Kriztel, Rudel, Mark Jayson, Jonathan | Richard, Kristine | Pool Car
2026-01-20 | 13:00 | 5:00 PM | BUDAC, TAYUM BRGY. HALL | AGN | ABRA | TAYUM | 64 | 4 | Gilbert, Cherry, Blessie, John Rey |  | Motor
2026-01-20 | 13:00 | 5:00 PM | BUNGRO BARANGAY HALL, BUNGRO, PINILI, ILOCOS NORTE | WDM | ILOCOS NORTE | PINILI | 45 | 4 | We-Ann, Arnelyn, Limwel, Alma | Rogen | Pool Car
2026-01-20 | 13:00 | 5:00 PM | LANCUAS COVERED COURT | ADM | ILOCOS SUR | SAN EMILIO | 32 | 4 | *Angelo, Recel, Dan, Domerson | Yolie | Pool Car
2026-01-20 | 13:00 | 5:00 PM | POB. SUR COVERED COURT | ADM | ILOCOS SUR | LIDLIDDA | 68 | 4 | *Natasha, Joy-Anne, Rodante, Renante, | Erol, Harry | Pool Car
2026-01-20 | 14:00 | 5:00 PM | SAN JUAN SARRAT COVERED COURT | MDL | ILOCOS NORTE | SARRAT | 114 | 4 | Joel, Glenn, Arvee, Jayzer |  | Motor
2026-01-20 | 14:00 | 5:00 PM | TANGAOAN BRGY HALL | MDL | ILOCOS NORTE | PIDDIG | 96 | 4 | Jerson, Ryan, Noble, Erl |  | Motor
2026-01-21 | 8:00 | 12:00 PM | TANGAOAN COVERED COURT, STA MARIA | HBR | ILOCOS SUR | STA MARIA | 104 | 3 | We-Ann, Arnelyn, Limwel | Richard, Yolie | Pool Car
2026-01-21 | 8:30 | 12:00 PM | MUNICIPAL COVERED COURT,NARVACAN I.S | RSG | ILOCOS SUR | NARVACAN | 684 | 13 | Kriztel, Rudel, Mark Jayson, Jonathan, Angelo, Recel, Dan, Domerson, Natasha, Joy-Anne, Rodante, Renante, Alma, (with Gilbert, Blessie, John Rey in the afternoon) | Harry, Kristine, Erol, Rogen | Pool Car
2026-01-21 | 8:00 | 12:00 PM | SAN JUAN EAST, PILAR BRGY. HALL | AGN | ABRA | PILAR | 49 | 4 | Gilbert, Cherry, Blessie, John Rey |  | Motor
2026-01-21 | 8:30 | 12:00 PM | DARUPIDIP, BRGY HALL | MDL | ILOCOS NORTE | PASUQUIN | 103 | 4 | Joel, Glenn, Arvee, Jayzer |  | Motor
2026-01-21 | 8:30 | 12:00 PM | LAGANDIT BRGY HALL | MDL | ILOCOS NORTE | PIDDIG | 91 | 4 | Jerson, Ryan, Noble, Erl |  | Motor
2026-01-21 | 14:00 | 5:00 PM | CALAMBEG BRGY HALL | MDL | ILOCOS NORTE | PIDDIG | 82 | 4 | Jerson, Ryan, Noble, Erl |  | Motor
2026-01-21 | 14:00 | 5:00 PM | SAN PEDRO COVERED COURT | MDL | ILOCOS NORTE | BATAC | 50 | 4 | Joel, Glenn, Arvee, Jayzer |  | Motor
2026-01-22 | 8:00 | 12:00 PM | CABAROAN COVERED COURT, STA MARIA | HBR | ILOCOS SUR | STA MARIA | 176 | 8 | Angelo, Recel, Dan, Domerson, Natasha, Joy-Anne, Rodante, Renante | Erol | Pool Car
2026-01-22 | 8:00 | 12:00 PM | NAGTENGNGA BRGY. PLAZA, STA CRUZ, ILOCOS SUR | JAD | ILOCOS SUR | STA CRUZ | 62 | 4 | We-Ann, Arnelyn, Limwel, Alma | Kristine, Harry | Pool Car
2026-01-22 | 8:00 | 12:00 PM | POBLACION, PILAR BRGY. HALL | AGN | ABRA | PILAR | 87 | 4 | Gilbert, Cherry, Blessie, John Rey |  | Motor
2026-01-22 | 8:00 | 12:00 PM | SAN MARCELINO BARANGAY HALL | WDS | ILOCOS NORTE | DINGRAS | 123 | 4 | Jerson, Ryan, Noble, Erl |  | Motor
2026-01-22 | 8:30 | 12:00 PM | SAN ANTONIO BRGY HALL | MDL | ILOCOS NORTE | PIDDIG | 65 | 4 | Joel, Glenn, Arvee, Jayzer |  | Motor
2026-01-22 | 9:00 | 12:00 PM | PALTOC COVERED COURT | ADM | ILOCOS SUR | SAN EMILIO | 57 | 4 | Kriztel, Rudel, Mark Jayson, Jonathan | Richard | Pool Car
2026-01-22 | 13:00 | 5:00 PM | BIDBIDAY BRGY. HALL | ACM | ILOCOS SUR | GALIMUYOD | 40 | 2 | We-Ann, Arnelyn | Kristine | Pool Car
2026-01-22 | 13:00 | 5:00 PM | BOROBOR BRGY. HALL | ACM | ILOCOS SUR | GALIMUYOD | 38 | 2 | Limwel, Alma | Harry | Pool Car
2026-01-22 | 13:00 | 5:00 PM | DALIT, PILAR BRGY. HALL | AGN | ABRA | PILAR | 38 | 2 | Cherry, John Rey |  | Motor
2026-01-22 | 13:00 | 5:00 PM | GARNADEN BARANGAY HALL, NUEVA ERA, ILOCOS NORTE | WDM | ILOCOS NORTE | NUEVA ERA | 39 | 4 | Jerson, Ryan, Noble, Erl |  | Motor
2026-01-22 | 13:00 | 5:00 PM | PALTOC COVERED COURT | ADM | ILOCOS SUR | SAN EMILIO | 34 | 4 | Kriztel, Rudel, Mark Jayson, Jonathan | Richard | Pool Car
2026-01-22 | 13:00 | 5:00 PM | TUQUIB, VIIAVICIOSA COVERED COURT | AGN | ABRA | VILLAVICIOSA | 38 | 2 | Gilbert, Blessie |  | Motor
2026-01-22 | 14:00 | 5:00 PM | ESTANCIA BRGY HALL | MDL | ILOCOS NORTE | PIDDIG | 40 | 4 | Joel, Glenn, Arvee, Jayzer |  | Motor
2026-01-23 | 8:00 | 12:00 PM | GUSING COVERED COURT, STA MARIA | HBR | ILOCOS SUR | STA MARIA | 102 | 6 | We-Ann, Arnelyn, Limwel, Alma, Kriztel, Domerson | Rogen | Pool Car
2026-01-23 | 8:00 | 12:00 PM | BESSANG COVERED COURT | ACM | ILOCOS SUR | BURGOS | 29 | 3 | Angelo, Mark Jayson, Jonathan | Erol | Pool Car
2026-01-23 | 8:00 | 12:00 PM | BITONG BRGY. HALL | ACM | ILOCOS SUR | GALIMUYOD | 30 | 4 | Recel, Dan, Rudel, Rodante | Harry | Pool Car
2026-01-23 | 8:00 | 12:00 PM | REYNALDO TABON RESIDENCE | ACM | ILOCOS SUR | BANAYOYO | 28 | 3 | Natasha, Joy-Anne, Renante | Yolie | Pool Car
2026-01-23 | 8:00 | 12:00 PM | SAN ISIDRO MUNICIPAL COVERED COURT | AGN | ABRA | SAN ISIDRO | 50 | 4 | Gilbert, Cherry, Blessie, John Rey |  | Motor
2026-01-23 | 9:00 | 12:00 PM | MADUPAYAS BARANGAY HALL, BADOC, ILOCOS NORTE | WDM | ILOCOS NORTE | BADOC | 36 | 4 | Joel, Glenn, Arvee, Jayzer |  | Motor
2026-01-23 | 13:00 | 5:00 PM | BAGBAGOTOT COVERED COURT | ACM | ILOCOS SUR | BANAYOYO | 7 | 3 | Natasha, Joy-Anne, Renante | Yolie | Pool Car
2026-01-23 | 13:00 | 5:00 PM | JACK BISALA RESIDENCE COSILI EAST-PROPER, BANGUED | AGN | ABRA | BANGUED | 11 | 2 | Gilbert, Blessie |  | Motor
2026-01-23 | 13:00 | 5:00 PM | LEGASPI BRGY. HALL | ACM | ILOCOS SUR | GALIMUYOD | 30 | 4 | Recel, Dan, Rudel, Rodante | Harry | Pool Car
2026-01-23 | 13:00 | 5:00 PM | SABANGAN PINGAN COVERED COURT | ACM | ILOCOS SUR | BURGOS | 40 | 3 | Angelo, Mark Jayson, Jonathan | Erol | Pool Car
2026-01-23 | 13:00 | 5:00 PM | SABTAN-OLO, SAN ISIDRO COVRERED COURT | AGN | ABRA | SAN ISIDRO | 29 | 2 | Cherry, John Rey |  | Motor
2026-01-23 | 14:00 | 5:00 PM | ALEJO MALASIG BRGY HALL | MDL | ILOCOS NORTE | VINTAR | 41 | 4 | Jerson, Ryan, Noble, Erl |  | Motor
2026-01-23 | 14:00 | 5:00 PM | UGUIS BARANGAY HALL, NUEVA ERA, ILOCOS NORTE | WDM | ILOCOS NORTE | NUEVA ERA | 88 | 4 | Joel, Glenn, Arvee, Jayzer |  | Motor
2026-01-24 | 8:00 | 12:00 PM | LUBING COVERED COURT | ACM | ILOCOS SUR | BURGOS | 17 | 2 | Kriztel, Domerson |  | Pool Car
2026-01-24 | 8:00 | 12:00 PM | LUNA COVERED COURT | ACM | ILOCOS SUR | BURGOS | 12 | 2 | Jerson, Joel |  | Motor
2026-01-24 | 8:00 | 12:00 PM | PANG-OT, PILAR BRGY. HALL | AGN | ABRA | PILAR | 55 | 4 | Gilbert, Cherry, Blessie, John Rey |  | Motor
2026-01-24 | 9:00 | 12:00 PM | BRGY. LEET - FL JERRY MOLINA RES. | RAG | PANGASINAN | STA BARBARA | 43 | 5 | Natasha, Joy-Anne, Recel, Rudel, Jonathan | Adrian, Jenny | Pool Car
2026-01-24 | 9:00 | 12:00 PM | FL RESIDENCE, CABITTAURAN, NUEVA ERA | WDM | ILOCOS NORTE | NUEVA ERA | 15 | 3 | Glenn, Arvee, Jayzer |  | Motor
2026-01-24 | 13:00 | 5:00 PM | BRGY. BANZAL - FL AGUSTIN MANUELK RES. | RAG | PANGASINAN | MAPANDAN, STA BARBARA | 57 | 5 | Natasha, Joy-Anne, Recel, Rudel, Jonathan | Adrian, Jenny | Pool Car
2026-01-24 | 13:00 | 5:00 PM | PATAC BRGY. HALL | ACM | ILOCOS SUR | CANDON, GALIMUYOD | 34 | 4 | We-Ann, Arnelyn, Limwel, Alma |  | Pool Car
2026-01-24 | 13:00 | 5:00 PM | TIKITIK, PILAR BRGY. HALL | AGN | ABRA | PILAR | 39 | 4 | Gilbert, Cherry, Blessie, John Rey |  | Motor
2026-01-26 | 8:00 | 12:00 PM | CATUCDAAN BRGY HALL, CABUGAO, ILOCOS SUR | WDM | ILOCOS SUR | CABUGAO | 29 | 3 | Jerson, Ryan, Erl |  | Motor
2026-01-26 | 8:00 | 12:00 PM | ROSIBEL GAYAO RESIDENCE | DPO | LA UNION | LUNA | 26 | 3 | Kriztel, Alma, Domerson | Richard, Kristine | Pool Car
2026-01-26 | 9:00 | 12:00 PM | BRGY. ANONANG - FL JUANITO SARATE RES. | RAG | PANGASINAN | SAN FABIAN | 27 | 3 | Natasha, Angelo, Recel | Rogen | Pool Car
2026-01-26 | 10:00 | 12:00 PM | ALINAAY BRGY HALL, CABUGAO, ILOCOS SUR | WDM | ILOCOS SUR | CABUGAO | 42 | 4 | Joel, Glenn, Arvee, Jayzer |  | Motor
2026-01-26 | 11:00 | 12:00 PM | BRGY. LABNEY - FL RODRIGO MANALO RES. | RAG | PANGASINAN | SAN JACINTO | 20 | 3 | Rudel, Jonathan, Rodante |  | Motor
2026-01-26 | 13:00 | 5:00 PM | CAELLAYAN BRGY HALL, CABUGAO, ILOCOS SUR | WDM | ILOCOS SUR | CABUGAO | 48 | 3 | Jerson, Ryan, Erl |  | Motor
2026-01-26 | 13:30 | 5:00 PM | BRGY ARAMAL FARMER'S COOP | RAG | PANGASINAN | SAN FABIAN | 22 | 3 | Natasha, Angelo, Recel | Rogen | Pool Car
2026-01-26 | 15:00 | 5:00 PM | PUG-OS BRGY HALL, CABUGAO, ILOCOS SUR | WDM | ILOCOS SUR | CABUGAO | 37 | 5 | Joel, Glenn, Arvee, Jayzer, John Rey |  | Motor
2026-01-26 | 15:30 | 5:00 PM | BRGY. MACAYUG - FC RENATO MOULIC RES | RAG | PANGASINAN | MANGALDAN | 8 | 3 | Rudel, Jonathan, Rodante |  | Motor
2026-01-27 | 8:00 | 12:00 PM | BRGY. HALL BANTAY INSIK | RAG | PANGASINAN | SISON | 6 | 2 | Rodante, Jonathan |  | Motor
2026-01-27 | 8:00 | 12:00 PM | PILA BRGY HALL, CABUGAO, ILOCOS SUR | WDM | ILOCOS SUR | CABUGAO | 76 | 5 | Jerson, Ryan, Erl, Jayzer, Blessie |  | Motor
2026-01-27 | 9:00 | 12:00 PM | SUYO MUNICIPAL HALL | DPO | ILOCOS SUR | SUYO | 75 | 4 | Kriztel, We-Ann, Alma, Domerson | Richard, Kristine | Pool Car
2026-01-27 | 10:00 | 12:00 PM | SALOMAGUE BRGY HALL, CABUGAO, ILOCOS SUR | WDM | ILOCOS SUR | CABUGAO | 46 | 3 | Joel, Glenn, Arvee |  | Motor
2026-01-27 | 11:00 | 12:00 PM | BRGY. PATAC - FC ALBERTO BALDEMOR RES. | RAG | LA UNION | STO TOMAS | 6 | 2 | *Rodante, Jonathan |  | Motor
2026-01-27 | 13:00 | 5:00 PM | BRGY. STA LUCIA - FC CHRISTOPHER HERRIRIA RES. | RAG | LA UNION | ARINGAY | 9 | 2 | *Rodante, Jonathan |  | Motor
2026-01-27 | 13:00 | 5:00 PM | CUANCABAL BRGY HALL, CABUGAO, ILOCOS SUR | WDM | ILOCOS SUR | CABUGAO | 59 | 5 | Jerson, Ryan, Erl, Jayzer, Blessie |  | Motor
2026-01-27 | 15:00 | 5:00 PM | BRGY. PANGAO-AOAN - FL ROGELIO RONQUILLO RES. | RAG | LA UNION | ARINGAY | 3 | 2 | *Rodante, Jonathan |  | Motor
2026-01-27 | 15:00 | 5:00 PM | CUANTACLA BRGY HALL, CABUGAO, ILOCOS SUR | WDM | ILOCOS SUR | CABUGAO | 52 | 4 | Joel, Glenn, Arvee, John Rey |  | Motor
2026-01-28 | 8:00 | 12:00 PM | STA CRUZ BRGY HALL, SINAIT, ILOCOS SUR | WDM | ILOCOS SUR | SINAIT | 41 | 5 | Joel, Glenn, Arvee, Jayzer, Erl |  | Motor
2026-01-28 | 8:00 | 12:00 PM | TALLIPUGO BRGY HALL | DPO | LA UNION | BALAOAN | 53 | 4 | Angelo, Recel, Rodante, Jonathan | Rogen | Pool Car
2026-01-28 | 10:00 | 12:00 PM | MASADAG BRGY HALL, SINAIT, ILOCOS SUR | WDM | ILOCOS SUR | SINAIT | 11 | 2 | Jerson, Ryan |  | Motor
2026-01-28 | 13:00 | 5:00 PM | BULBULALA BRGY HALL | DPO | LA UNION | BALAOAN | 56 | 4 | Angelo, Recel, Rodante, Jonathan | Rogen | Pool Car
2026-01-28 | 13:00 | 5:00 PM | CURTIN BRGY HALL, SINAIT, ILOCOS SUR | WDM | ILOCOS SUR | SINAIT | 65 | 5 | Joel, Glenn, Arvee, Jayzer, Erl |  | Motor
2026-01-29 | 9:00 | 12:00 PM | BULALAAN BRGY HALL | DPO | LA UNION | SUDIPEN | 15 | 3 | Kriztel, Alma, Domerson | Richard, Kristine | Pool Car
2026-01-29 | 9:00 | 12:00 PM | CARAISAN BARANGAY HALL, MAGSINGAL, ILOCOS NORTE | WDM | ILOCOS SUR | MAGSINGAL | 42 | 4 | Joel, Glenn, Arvee, Jayzer |  | Motor
2026-01-29 | 9:00 | 12:00 PM | CARAISAN BARANGAY HALL, MAGSINGAL, ILOCOS NORTE | WDM | ILOCOS SUR | SAN JUAN | 2 | 4 | Joel, Glenn, Arvee, Jayzer |  | Motor
2026-01-29 | 13:00 | 5:00 PM | CASTRO COVERED COURT | DPO | LA UNION | SUDIPEN | 29 | 3 | Kriztel, Alma, Domerson | Richard, Kristine | Pool Car
2026-01-29 | 13:00 | 5:00 PM | PATONG BARANGAY HALL, MAGSINGAL, ILOCOS NORTE | WDM | ILOCOS SUR | MAGSINGAL | 45 | 4 | Jerson, Ryan, Noble, Erl |  | Motor
2026-01-30 | 9:00 | 12:00 PM | STO DOMINGO COLISEUM, POBLACION, STO DOMINGO | WDM | ILOCOS SUR | STO DOMINGO | 121 | 8 | Joel, Glenn, Arvee, Jayzer, Jerson, Ryan, Erl, Blessie |  | Motor

## Unscheduled
Date | Time Start | Time End | Venue | PM | Province | Municipality | Target
2026-01-19 | 8:00 | 12:00 PM | BAGANI UBBOG BARANGAY PLAZA | RVR | ILOCOS SUR | CANDON | 50
2026-01-19 | 8:00 | 12:00 PM | BOMITOG BARANGAY HALL | WDS | ILOCOS NORTE | BANNA | 135
2026-01-19 | 8:00 | 12:00 PM | CABAROAN BRGY. HALL | ACM | ILOCOS SUR | SAN ESTEBAN | 23
2026-01-19 | 8:00 | 12:00 PM | DACUTAN COVERED COURT | DPO | ILOCOS SUR | TAGUDIN | 26
2026-01-19 | 8:00 | 12:00 PM | LANG-AYAN, COVERED COURT | ACM | ILOCOS SUR | SANTIAGO | 28
2026-01-19 | 8:00 | 12:00 PM | NAGPANAOAN COVERED COURT | ACM | ILOCOS SUR | BURGOS | 47
2026-01-19 | 8:00 | 12:00 PM | BOLBOLO, PILAR BRGY. HALL | AGN | ABRA | PILAR | 81
2026-01-19 | 8:00 | 12:00 PM | TUBO MUNICIPAL NURSERY | AGN | ABRA | TUBO | 39
2026-01-19 | 8:30 | 12:00 PM | BUNGON COMMUNITY CENTER | MDL | ILOCOS NORTE | BATAC | 34
2026-01-19 | 9:00 | 12:00 PM | SAN FELIPE BRGY. HALL | RAG | TARLAC | MONCADA, SAN MANUEL | 53
2026-01-19 | 13:00 | 5:00 PM | BINACAG BARANGAY HALL | WDS | ILOCOS NORTE | BANNA | 34
2026-01-19 | 13:00 | 5:00 PM | CABCABURAO COVERED COURT | ACM | ILOCOS SUR | BURGOS | 77
2026-01-19 | 13:00 | 5:00 PM | CAPPA-CAPPA BRGY. HALL | ACM | ILOCOS SUR | CANDON, SAN ESTEBAN | 26
2026-01-19 | 13:00 | 5:00 PM | MAMBUG COVERED COURT | ACM | ILOCOS SUR | SANTIAGO | 23
2026-01-19 | 13:00 | 5:00 PM | MANGANDINGAY BRGY HALL | RAG | TARLAC | SAN MANUEL | 12
2026-01-19 | 13:00 | 5:00 PM | RANGET BRGY HALL | DPO | ILOCOS SUR | TAGUDIN | 53
2026-01-19 | 13:00 | 5:00 PM | RAPANUT, ORLANDO GALANTO RESIDENCE | RVR | ILOCOS SUR | CANDON | 16
2026-01-19 | 14:00 | 5:00 PM | BULBULALA BRGY HALL | MDL | ILOCOS NORTE | VINTAR | 24
2026-01-19 | 15:00 | 5:00 PM | BRGY. STA MONICA - FL ROLANDO BACANI RES. | RAG | TARLAC | MONCADA | 24
2026-01-20 | 8:00 | 12:00 PM | ALILEM MINI CONVENTION CENTER | DPO | ILOCOS SUR | ALILEM | 81
2026-01-20 | 8:00 | 12:00 PM | ALINAYA, PIDIGAN BRGY. HALL/COVERED COURT | AGN | ABRA | PIDIGAN | 23
2026-01-20 | 8:00 | 12:00 PM | ANSAD BRGY. HALL | ACM | ILOCOS SUR | SAN ESTEBAN | 40
2026-01-20 | 8:00 | 12:00 PM | BACSIL BARANGAY HALL | WDS | ILOCOS NORTE | DINGRAS | 25
2026-01-20 | 8:00 | 12:00 PM | BANAY, BRGY. PLAZA, STA CRUZ, ILOCOS SUR | JAD | ILOCOS SUR | STA CRUZ | 44
2026-01-20 | 8:00 | 12:00 PM | BULBULALA COVERED COURT | ACM | ILOCOS SUR | SANTIAGO | 29
2026-01-20 | 8:00 | 12:00 PM | BULICLIC BRGY. PLAZA, STA LUCIA, ILOCOS SUR | JAD | ILOCOS SUR | STA LUCIA | 35
2026-01-20 | 8:00 | 12:00 PM | GADONG, RENATO GRAMAJE RESIDENCE | RVR | ILOCOS SUR | CANDON | 27
2026-01-20 | 8:00 | 12:00 PM | LAP-LAPOG, VILLAVICIOSA FARMERS TRAINING CENTER | AGN | ABRA | VILLAVICIOSA | 74
2026-01-20 | 8:00 | 12:00 PM | MANABOC COVERED COURT | ACM | ILOCOS SUR | BURGOS | 59
2026-01-20 | 8:00 | 12:00 PM | NAGPATAYAN BARANGAY HALL | WDS | ILOCOS NORTE | BANNA | 52
2026-01-20 | 8:00 | 12:00 PM | PARIOC SEGUNDO BARANGAY PLAZA | RVR | ILOCOS SUR | CANDON | 56
2026-01-20 | 8:00 | 12:00 PM | POB. SUR COVERED COURT | ADM | ILOCOS SUR | LIDLIDDA | 49
2026-01-20 | 8:00 | 12:00 PM | SOUTH BALIOAG, PILAR COVERED COURT | AGN | ABRA | PILAR | 19
2026-01-20 | 8:30 | 12:00 PM | ESTEBENSON, PDRON RES. | MDL | ILOCOS NORTE | BACARRA | 84
2026-01-20 | 8:30 | 12:00 PM | ISIC-ISIC BRGY HALL | MDL | ILOCOS NORTE | VINTAR | 68
2026-01-20 | 9:00 | 12:00 PM | BRGY TOLEGA NORTE - FC LORETO BARTOLOME RES. | RAG | TARLAC | MONCADA | 27
2026-01-20 | 9:00 | 12:00 PM | POBLACION-MADAYAO, SIGAY, ILOCOS SUR | ADM | ILOCOS SUR | SIGAY | 17
2026-01-20 | 9:00 | 12:00 PM | TIAGAN COVERED COURT | ADM | ILOCOS SUR | SAN EMILIO | 55
2026-01-20 | 13:00 | 5:00 PM | BAGAR BARANGAY PLAZA | RVR | ILOCOS SUR | CANDON | 26
2026-01-20 | 13:00 | 5:00 PM | BRGY. COLIBANGBANG - FC CHRISTIAN CAINGLET RES. | RAG | TARLAC | PANIQUI | 6
2026-01-20 | 13:00 | 5:00 PM | CAL-LAO, VILLAVICIOSA COVERED COURT | AGN | ABRA | VILLAVICIOSA | 33
2026-01-20 | 13:00 | 5:00 PM | CALONGBUYAN BRGY. HALL | ACM | ILOCOS SUR | CANDON, GALIMUYOD | 38
2026-01-20 | 13:00 | 5:00 PM | CONCEPCION, BRGY. HALL | ADM | ILOCOS SUR | GREGORIO DEL PILAR | 67
2026-01-20 | 13:00 | 5:00 PM | CUBCUBBOOT BARANGAY PLAZA | RVR | ILOCOS SUR | CANDON | 53
2026-01-20 | 13:00 | 5:00 PM | IMELDA BARANGAY HALL | WDS | ILOCOS NORTE | BANNA | 42
2026-01-20 | 13:00 | 5:00 PM | LANTAG BRGY. PLAZA, STA CRUZ, ILOCOS SUR | JAD | ILOCOS SUR | STA CRUZ | 23
2026-01-20 | 13:00 | 5:00 PM | NAMATICAN BRGY. PLAZA, STA LUCIA, ILOCOS SUR | JAD | ILOCOS SUR | STA LUCIA | 62
2026-01-20 | 13:00 | 5:00 PM | NARNARA, PILAR COVERED COURT | AGN | ABRA | PILAR | 10
2026-01-20 | 13:00 | 5:00 PM | OLD CENTRAL BRGY HALL | DPO | LA UNION | SUDIPEN | 17
2026-01-20 | 13:00 | 5:00 PM | SALINCUB COVERED COURT | ACM | ILOCOS SUR | SANTIAGO | 27
2026-01-20 | 13:00 | 5:00 PM | SALUDARES BARANGAY HALL | WDS | ILOCOS NORTE | DINGRAS, MARCOS | 17
2026-01-20 | 13:00 | 5:00 PM | SITIO NAGDAINGAN PANTUD, PIDIGAN BRGY. HALL/ COVERED COURT | AGN | ABRA | PIDIGAN | 47
2026-01-20 | 14:00 | 5:00 PM | CABAYO BRGY HALL | MDL | ILOCOS NORTE | VINTAR | 44
2026-01-20 | 14:00 | 5:00 PM | COLUMBIA BRGY HALL | MDL | ILOCOS NORTE | VINTAR | 52
2026-01-21 | 8:00 | 12:00 PM | ARAB, PIDIGAN BRGY. HALL | AGN | ABRA | PIDIGAN | 24
2026-01-21 | 8:00 | 12:00 PM | AR-ARAMPANG COVERED COURT | DPO | LA UNION | BALAOAN | 41
2026-01-21 | 8:00 | 12:00 PM | BARBARANGAY BARANGAY HALL | WDS | ILOCOS NORTE | BANNA | 51
2026-01-21 | 8:00 | 12:00 PM | BOLILISING, VILLAVICIOSA COVERED COURT | AGN | ABRA | VILLAVICIOSA | 24
2026-01-21 | 8:00 | 12:00 PM | BUCLOC MUNICIPAL HALL | AGN | ABRA | BUCLOC | 14
2026-01-21 | 8:00 | 12:00 PM | BUGBUGA BRGY. PLAZA, STA CRUZ, ILOCOS SUR | JAD | ILOCOS SUR | STA CRUZ | 85
2026-01-21 | 8:00 | 12:00 PM | CALLITONG COVERED COURT | ACM | ILOCOS SUR | BURGOS | 31
2026-01-21 | 8:00 | 12:00 PM | CALUMBAYA BRGY. HALL | ACM | ILOCOS SUR | GALIMUYOD | 43
2026-01-21 | 8:00 | 12:00 PM | CATANGRARAN BARANGAY HALL | WDS | ILOCOS NORTE | SOLSONA | 29
2026-01-21 | 8:00 | 12:00 PM | CATERMAN BARANGAY PLAZA | RVR | ILOCOS SUR | CANDON | 34
2026-01-21 | 8:00 | 12:00 PM | EDGARDO ANGA-ANGAN RESIDENCE | ACM | ILOCOS SUR | SANTIAGO | 22
2026-01-21 | 8:00 | 12:00 PM | LABUT COVERED COURT | ADM | ILOCOS SUR | LIDLIDDA | 29
2026-01-21 | 8:00 | 12:00 PM | NAGCANASAN, PILAR COVERED COURT | AGN | ABRA | PILAR | 14
2026-01-21 | 8:00 | 12:00 PM | PALALI SUR BRGY. PLAZA, STA LUCIA, ILOCOS SUR | JAD | ILOCOS SUR | STA LUCIA | 40
2026-01-21 | 8:30 | 12:00 PM | CALANGCUASAN BARANGAY PLAZA | RVR | ILOCOS SUR | SALCEDO | 34
2026-01-21 | 8:30 | 12:00 PM | DIPILAT BRGY HALL | MDL | ILOCOS NORTE | VINTAR | 31
2026-01-21 | 8:30 | 12:00 PM | SAN MATEO COMMUNITY CENTER | MDL | ILOCOS NORTE | BATAC | 57
2026-01-21 | 9:00 | 12:00 PM | ALFONSO COVERED COURT | ADM | ILOCOS SUR | GREGORIO DEL PILAR | 61
2026-01-21 | 9:00 | 12:00 PM | BRGY. HALL VACANTE | RAG | PANGASINAN | ALCALA | 41
2026-01-21 | 9:00 | 12:00 PM | CAYUS COVERED COURT | ADM | ILOCOS SUR | QUIRINO | 47
2026-01-21 | 9:00 | 12:00 PM | TIAGAN COVERED COURT | ADM | ILOCOS SUR | SAN EMILIO | 14
2026-01-21 | 9:00 | 12:00 PM | TUROD BARANGAY HALL, TUROD, BADOC, ILOCOS NORTE | WDM | ILOCOS NORTE | BADOC | 50
2026-01-21 | 13:00 | 5:00 PM | BALUGANG COVERED COURT | ACM | ILOCOS SUR | BURGOS | 15
2026-01-21 | 13:00 | 5:00 PM | BRGY. HALL SAN PEDRO APARTADO | RAG | PANGASINAN | ALCALA | 27
2026-01-21 | 13:00 | 5:00 PM | CARIBQUIB BARANGAY HALL | WDS | ILOCOS NORTE | BANNA | 45
2026-01-21 | 13:00 | 5:00 PM | MANALPAC (DANILO MACNI RESIDENCE) | WDS | ILOCOS NORTE | SOLSONA | 34
2026-01-21 | 13:00 | 5:00 PM | ORTEGA COVERED COURT | DPO | LA UNION | BACNOTAN | 58
2026-01-21 | 13:00 | 5:00 PM | PADUROS COVERED COURT | ACM | ILOCOS SUR | BURGOS | 17
2026-01-21 | 13:00 | 5:00 PM | GAPANG, PILAR GYMNASIUM | AGN | ABRA | PILAR | 45
2026-01-21 | 13:00 | 5:00 PM | SALLAPADAN DA OFFICE | AGN | ABRA | SALLAPADAN | 13
2026-01-21 | 13:00 | 5:00 PM | SAN PEDRO BRGY. PLAZA, STA CRUZ, ILOCOS SUR | JAD | ILOCOS SUR | STA CRUZ | 90
2026-01-21 | 13:00 | 5:00 PM | SAPANG BRGY. PLAZA, STA LUCIA, ILOCOS SUR | JAD | ILOCOS SUR | STA LUCIA | 69
2026-01-21 | 13:00 | 5:00 PM | SITIO DAGMAN COVERED COURT | ADM | ILOCOS SUR | QUIRINO | 68
2026-01-21 | 13:00 | 5:00 PM | SORIOAN BARANGAY PLAZA | RVR | ILOCOS SUR | SALCEDO | 45
2026-01-21 | 13:00 | 5:00 PM | TABLAC BARANGAY PLAZA | RVR | ILOCOS SUR | CANDON | 65
2026-01-21 | 13:00 | 5:00 PM | TOON, LA PAZ BRGY. HALL/COVERED COURT | AGN | ABRA | DANGLAS, LA PAZ, LANGIDEN | 36
2026-01-21 | 13:00 | 5:00 PM | TUBALINA COVERED COURT | ADM | ILOCOS SUR | GREGORIO DEL PILAR | 19
2026-01-21 | 13:00 | 5:00 PM | UBBOG COVERED COURT | ACM | ILOCOS SUR | SANTIAGO | 12
2026-01-21 | 14:00 | 5:00 PM | STA CRUZ SUR BARANGAY HALL, BADOC, ILOCOS NORTE | WDM | ILOCOS NORTE | BADOC | 32
2026-01-21 | 14:00 | 5:00 PM | VISAYA BRGY HALL | MDL | ILOCOS NORTE | VINTAR | 11
2026-01-21 | 15:00 | 5:00 PM | BRGY. HALL PINDANGAN CENTRO | RAG | PANGASINAN | ALCALA | 24
2026-01-22 | 8:00 | 12:00 PM | AGTIPAL BRGY HALL | DPO | LA UNION | BACNOTAN | 19
2026-01-22 | 8:00 | 12:00 PM | ANDREA REYES RESIDENCE | ACM | ILOCOS SUR | BANAYOYO | 30
2026-01-22 | 8:00 | 12:00 PM | BARIT, LUBA BRGY. HALL/ COVERED COURT | AGN | ABRA | LUBA | 62
2026-01-22 | 8:00 | 12:00 PM | DIRDIRIG COVERED COURT | ACM | ILOCOS SUR | BURGOS | 41
2026-01-22 | 8:00 | 12:00 PM | GAPANG, PILAR BRGY. HALL | AGN | ABRA | PILAR | 2
2026-01-22 | 8:00 | 12:00 PM | LANGLANGCA PRIMERO BARANGAY PLAZA | RVR | ILOCOS SUR | BANAYOYO, CANDON | 50
2026-01-22 | 8:00 | 12:00 PM | NAGREBCAN BRGY. PLAZA, STA LUCIA, ILOCOS SUR | JAD | ILOCOS SUR | STA LUCIA | 29
2026-01-22 | 8:00 | 12:00 PM | POBLACION, LICUAN-BAAY BRGY. HALL | AGN | ABRA | LICUAN-BAAY | 13
2026-01-22 | 8:30 | 12:00 PM | BANGUI MUNICIPAL AGRICULLTURE OFFICE | MDL | ILOCOS NORTE | BANGUI | 62
2026-01-22 | 8:30 | 12:00 PM | DAGUPAN BRGY HALL | MDL | ILOCOS NORTE | VINTAR | 34
2026-01-22 | 8:30 | 12:00 PM | JIMENEZ, RUFO PEDRITO RESIDENCE | RVR | ILOCOS SUR | SALCEDO | 9
2026-01-22 | 9:00 | 12:00 PM | BRGY. HALL SAN NARCISO | RAG | PANGASINAN | STO TOMAS, SAN MANUEL | 58
2026-01-22 | 9:00 | 12:00 PM | CAMANGA BARANGAY HALL, BADOC, ILOCOS NORTE | WDM | ILOCOS NORTE | BADOC | 65
2026-01-22 | 9:00 | 12:00 PM | DA EXTENSION OFFICE,NAGSANGALAN VIGAN CITY | RSG | ILOCOS SUR | SAN VICENTE, VIGAN | 30
2026-01-22 | 13:00 | 5:00 PM | BRGY. HALL SAN RAYMUNDO | RAG | PANGASINAN | BALUNGAO, ROSALES, STA MARIA | 37
2026-01-22 | 13:00 | 5:00 PM | CAPARIAAN BRGY. PLAZA, STA CRUZ, ILOCOS SUR | JAD | ILOCOS SUR | STA CRUZ | 20
2026-01-22 | 13:00 | 5:00 PM | CULIONG BARANGAY PLAZA | RVR | ILOCOS SUR | SALCEDO | 32
2026-01-22 | 13:00 | 5:00 PM | DANGDANGLA BRGY HALL | DPO | LA UNION | SAN JUAN | 19
2026-01-22 | 13:00 | 5:00 PM | ESCODA BARANGAY HALL | WDS | ILOCOS NORTE | DINGRAS, MARCOS | 23
2026-01-22 | 13:00 | 5:00 PM | LANGLANGCA SEGUNDO BARANGAY PLAZA | RVR | ILOCOS SUR | CANDON | 15
2026-01-22 | 13:00 | 5:00 PM | NAGUIMBA COVERED COURT | ACM | ILOCOS SUR | BANAYOYO | 24
2026-01-22 | 13:00 | 5:00 PM | POB., LUBA BRGY. HALL/COVERED COURT | AGN | ABRA | LUBA | 17
2026-01-22 | 13:00 | 5:00 PM | TALIAO COVERED COURT | ACM | ILOCOS SUR | BURGOS | 19
2026-01-22 | 14:00 | 5:00 PM | BUDUAN BRGY HALL | MDL | ILOCOS NORTE | BURGOS | 63
2026-01-22 | 14:00 | 5:00 PM | ESPERANZA BRGY HALL | MDL | ILOCOS NORTE | VINTAR | 24
2026-01-23 | 8:00 | 12:00 PM | CADAANAN DINTAN,PILAR TREE PARK | AGN | ABRA | PILAR | 31
2026-01-23 | 8:00 | 12:00 PM | LABON, BUCAY COVERED COURT | AGN | ABRA | BUCAY | 14
2026-01-23 | 8:00 | 12:00 PM | MANAYDAY, SAN ISIDRO COVERED COURT | AGN | ABRA | SAN ISIDRO | 16
2026-01-23 | 8:00 | 12:00 PM | PATAD, PILAR COVERED COURT | AGN | ABRA | PILAR | 32
2026-01-23 | 8:00 | 12:00 PM | SAN FRANCISCO SUR COVERED COURT | DPO | LA UNION | SUDIPEN | 32
2026-01-23 | 9:00 | 12:00 PM | BRGY. HALL CARAMUTAN | RAG | PANGASINAN | ASINGAN, VILLASIS | 19
2026-01-23 | 9:00 | 12:00 PM | CARASI, MUNICIPAL HALL | MDL | ILOCOS NORTE | CARASI | 24
2026-01-23 | 9:00 | 12:00 PM | DAMPIG BRGY HALL | MDL | ILOCOS NORTE | PAGUDPUD | 3
2026-01-23 | 9:30 | 12:00 PM | LIBANG BRGY HALL | ADM | ILOCOS SUR | CERVANTES | 5
2026-01-23 | 13:00 | 5:00 PM | BRGY. HALL DOMINGO ALARCIO | RAG | PANGASINAN | LAOAC | 4
2026-01-23 | 13:00 | 5:00 PM | SINAPANGAN SUR COVERED COURT | DPO | LA UNION | BANGAR | 27
2026-01-23 | 13:00 | 5:00 PM | SITIO BUCNIT COVERED COURT | ADM | ILOCOS SUR | QUIRINO | 33
2026-01-23 | 15:00 | 5:00 PM | BRGY. NANBAGATAN - FC FRANCISCA PAULINO RES. | RAG | PANGASINAN | LAOAC | 17
2026-01-24 | 8:00 | 12:00 PM | FL LIOVIE PASCUAL RESIDENCE TANGADAN, SAN QUINTIN | AGN | ABRA | SAN QUINTIN | 30
2026-01-24 | 13:00 | 5:00 PM | PANTOC, SAN QUINTIN BRGY. HALL/COVERED COURT | AGN | ABRA | SAN QUINTIN | 52
2026-01-24 | 15:00 | 5:00 PM | BRGY. SAN RAMON - FC EDWIN EUFEMIANO RES. | RAG | PANGASINAN | MANAOAG | 5
2026-01-26 | 14:00 | 5:00 PM | DIONISIO SANTIAGO RESIDENCE | DPO | LA UNION | SAN GABRIEL | 7
2026-01-28 | 9:00 | 12:00 PM | BRGY. HALL NARRA OESTE | RAG | LA UNION | SAN FERNANDO | 1
2026-01-28 | 15:00 | 5:00 PM | BARABAC BRGY HALL, SINAIT, ILOCOS SUR | WDM | ILOCOS SUR | SINAIT | 2
2026-01-28 | 15:00 | 5:00 PM | BRGY. SACYUD - FC WARLITO ESPIRITU RES. | RAG | LA UNION | SAN FERNANDO | 1
2026-01-29 | 8:00 | 12:00 PM | BRGY. LIOAC SUR | RAG | LA UNION | NAGUILIAN | 5
2026-01-29 | 13:00 | 5:00 PM | BRGY. RIZAL - FC ROMEO GALISTE RES. | RAG | LA UNION | TUBAO | 2